## Sheet1
Initiative | Category | Track | Quarter | PlannedStart | PlannedEnd | ActualStart | ActualEnd | Status | Revenue | Effort | BreakEvenMonths | Module
Budget Constraints Planning | New Feature | DDE | 2025-Q3 | 2025-06-01 | 2025-07-15 | 2025-06-01 | 2025-07-10 | Completed | 120 | 420 | 8 | Planning
Target KPI Multidimension | New Feature | DDE | 2025-Q3 | 2025-06-15 | 2025-08-01 | 2025-06-17 | 2025-08-05 | Completed | 150 | 520 | 9 | Planning
Export/Import Planned Outputs | Enhancement | DDE | 2025-Q3 | 2025-07-01 | 2025-07-25 | 2025-07-02 | 2025-07-26 | Completed | 40 | 120 | 4 | Planning
Multiplicative Model Form | Algorithm | DDE | 2025-Q3 | 2025-08-01 | 2025-09-15 | 2025-08-05 | 2025-09-25 | In Progress | 85 | 300 | 7 | Modelling
Auto Refresh Extend Coefficients | Feature | AI/Automation | 2025-Q3 | 2025-09-01 | 2025-10-15 |  |  | Planned | 60 | 200 | 6 | Modelling
Batch Edit Saturation Params | Enhancement | DDE | 2025-Q3 | 2025-09-10 | 2025-10-30 |  |  | Planned | 55 | 180 | 5 | Modelling
LT Multiplier in Reporting | Feature | DDE | 2025-Q3 | 2025-10-01 | 2025-11-20 |  |  | Planned | 95 | 260 | 6 | Reporting
Outlier Detection in EDA (POC) | Feature | AI/Automation | 2025-Q3 | 2025-07-05 | 2025-08-05 | 2025-07-06 | 2025-08-12 | Completed | 30 | 100 | 3 | EDA
Custom Project Calendar (4-4-5) | Feature | DDE | 2025-Q3 | 2025-08-10 | 2025-10-10 |  |  | In Progress | 70 | 240 | 6 | Project
PNG Download for Outputs | Enhancement | DDE | 2025-Q3 | 2025-07-10 | 2025-07-20 | 2025-07-11 | 2025-07-19 | Completed | 20 | 80 | 2 | Overall